## Sheet1
SL NO | TASK | JIRA | Owner | Estimate | Start Date | Expected End Date | Current Status | Sprint Name
1 | GitHub JWT Integration | 1234 | Developer 1 | 2 Days | 2021-10-20 | 2021-10-22 | IN PROGRESS | October-Spring
2 | Data Mode for Customer | 1235 | Developer 2 | 5 Days | 2021-10-21 | 2021-10-26 | IN PROGRESS | October-Spring
3 | Ticket Booking REST API | 1236 | Developer 1 | 3 Days | 2021-10-23 | 2021-10-26 | IN PROGRESS | October-Spring
4 | Ticket Booking Repository Implementation | 1237 | Developer 2 | 3 Days | 2021-10-26 | 2021-10-29 | IN PROGRESS | October-Spring